Practice Name:

| PIP QI quarter: please tick ü | Quarter 1 Nov – Jan ☐ | Quarter 2 Feb – Apr ☒ | Quarter 3 May – Jul ☐ | Quarter 4 Aug – Oct ☐ |
| --- | --- | --- | --- | --- |
| Date: _________ |  |  |  |  |
| Name of QIA: | Increase the uptake of Health Assessments among Aboriginal and Torres Strait Islander People. |  |  |  |

| - PLAN |  |  |  |
| --- | --- | --- | --- |
| - Goal | - <What are we trying to accomplish and when? Make the goal simple, measurable, achievable, realistic and timely> We will complete 15 MBS Item 715 Health Assessments for eligible Aboriginal and Torres Strait Islander patients by DD/MM/YYYY |  |  |
| - Baseline Data: | - <What is our current data saying?> xx patients eligible for MBS Item 715 Health Assessments completed as per CESPHN MBS Opportunity Report from (dd/mm/yyyy) |  |  |
| - Data to be collected: | - <What data will we use to track our improvement?> To measure the improvements, we will use POLAR QIPC report > Tracked MBS> Indigenous Health Assessment • The number of patients who are eligible for a 715 Health Assessment initially and, - • The number of patients who have a 715 health assessment completed. |  |  |
| - Steps for Implementation |  |  |  |
| - What |  | - Who | - By When |
| - 1. Organise a training session to demonstrate correct data entry in Clinical Software (no free text in Progress Notes) |  |  |  |
| - 2. Trial post it notes in consult rooms as a prompt to update opportunistically e.g. during GPCCMP, Health Assessment |  |  |  |
| - 3. Put on the agenda for next Clinical Meeting – team-based discussion to gain insight into current workflows and barriers - djnf |  |  |  |
| - 4. Improve New Patient Registration Form and trial for 1 month |  |  |  |
| - 5. Reception to review completed patient forms and gently prompt when Social and Family History not provided |  |  |  |
| - 6. Download Walrus – point of care prompt tool (part of our POLAR licence) |  |  |  |

- DO – Insert any observations you had during implementation of this plan

<Did you do it? Insert any observations you had during implementation of this plan, unforeseen amendments, unexpected events> Example: Mid-February: A baseline health assessment report was generated using the practice’s data extraction tool to identify eligible Aboriginal and Torres Strait Islander patients who had not had a 715 Health Assessment in the previous 12 months. Following week: The eligibility list was cross-checked against Medicare/HPOS records to ensure patients had not completed a health assessment elsewhere. Late February: Eligible patients were contacted via SMS and/or phone calls inviting them to book a 715 Health Assessment. Early March: The first health assessments were completed. During one assessment, additional chronic disease risk factors were identified, and appropriate referrals were arranged. This demonstrated the benefit of structured preventive screening and prompted the team to streamline referral processes during assessments. Mid-March: A progress report was re-run to monitor uptake. A small increase in completed health assessments was noted, which reassured the team that the recall strategy was effective. Early April: A GP identified an eligible patient opportunistically during a routine consultation and encouraged booking a 715 assessment. This reinforced the importance of opportunistic offers in addition to recall systems. Late April: A follow-up report showed steady progress, including patients who had been contacted and those identified opportunistically. May: Continued monitoring demonstrated a noticeable increase in completed assessments. Positive feedback was shared with the team to maintain engagement and motivation. June: Unforeseen staff illness and leave resulted in some appointments being rescheduled, temporarily slowing progress. Data extraction for that month was delayed. July: Reporting resumed, and a modest increase in completed health assessments was observed, consistent with the reduced clinical capacity during the previous period. August: Final review of the reporting cycle showed a sustained increase in total completed 715 Health Assessments compared to baseline. The recall system and opportunistic offering were both contributing to improved uptake.

- STUDY Reflections, knowledge gained, effectiveness of improvement

- <Reflections: knowledge gained, effectiveness of improvement, measurement goals, potential changes that could be made in the next cycle> The test worked well and achieved a great result. We anticipated that we would complete 15 health assessments and we ended up completing a total of 17 health assessments which surpassed our expectations. - Some GPs in our practice have expressed interest in learning more about the Integrated Team Care (ITC) program for Aboriginal and Torres Strait Islander people, including its components of care coordination, supplementary services, and outreach support. We have invited CESPHN to deliver an education session for the entire practice team to build understanding and support implementation.

- ACT - Next steps? Record the details of your option under the relevant heading

<Next steps? Record the details of your option under the relevant heading below > ADOPT - record what you will do next to support making this change business as usual Partner with CESPHN for Care Coordination - Engage with Central and Eastern Sydney Primary Health Network to: - Link patients identified through 715 assessments to care coordination programs - Support patients with complex or chronic conditions - Improve access to allied health, mental health, and social support services - Establish referral pathways from 715 assessments directly into CESPHN-supported programs ADAPT - record your changes and re-test with another PDSA cycle ABANDON - record which change idea you will test next and start a new PDSA.

- Evidence of improvement.

<Screenshots from extraction tool, Practice Progress Report>