Practice Name:

| PIP QI quarter: please tick ü | Quarter 1 Nov – Jan ​☐ | Quarter 2 Feb – Apr ☒ | Quarter 3 May – Jul ​ ☐ ​ | Quarter 4 Aug – Oct ​ ☐ |
| --- | --- | --- | --- | --- |
| Date: _________ |  |  |  |  |
| Name of QIA: | Improving coding of diabetes to support MyMedicare enrolment. |  |  |  |

| - PLAN |  |  |  |
| --- | --- | --- | --- |
| - Goal | - <What are we trying to accomplish and when? Make the goal simple, measurable, achievable, realistic and timely> - Decrease the number of active patients who have suspected diabetes mellitus from 2646 to 2000 within 3 months. |  |  |
| - Baseline Data: | - <What is our current data saying?> - Active patients= 10 612 - Coded Diabetes= 789 - Suspected Diabetes Mellitus=1261 - Source: POLAR Clinic Summary Report > Clinical > Diabetes QI > Most Recent Coded Diabetes |  |  |
| - Data to be Collected: | - <What data will we use to track our improvement?> - We will run monthly POLAR audits to track: - Number of patients remaining in ‘indicated diabetes’ category - Number of patients newly coded with diabetes |  |  |
| - Steps for Implementation |  |  |  |
| - What |  | - Who | - By When |
| - Run POLAR audit to identify a list of patients with indicated diabetes |  | - Practice manager |  |
| - Train staff on best practices for chronic conditions coding |  | - GP, PHN DHO |  |
| - Conduct targeted clinical record reviews to confirm diagnosis using pathology, medications, and clinical history. |  | - Nurse |  |
| - Implement recall system for patients requiring further investigation (e.g. HbA1c) |  | - Nurse |  |
| - Include MyMedicare enrolment as a part of review process |  | - Practice Manager |  |

- DO

<Did you do it? Insert any observations you had during implementation of this plan, unforeseen amendments, unexpected events> - Generated a POLAR report identifying 1261 patients with indicated diabetes and created a working patient list - Provided staff training on best practices for chronic condition coding, diabetes diagnostic criteria, and the importance of accurate coding to support MyMedicare enrolment - Conducted targeted clinical record reviews, confirming diagnoses using pathology, medications, and clinical history, and updated coding where criteria were met - Implemented a recall system (SMS followed by phone calls) for patients requiring further investigation (e.g. HbA1c testing) - Integrated MyMedicare enrolment into the review process, with eligible patients offered enrolment following diagnosis or during follow-up

- STUDY

- <Reflections: knowledge gained, effectiveness of improvement, measurement goals, potential changes that could be made in the next cycle> - Reduction in patients with indicated diabetes from 1261 to 900 - A significant number of patients had sufficient clinical evidence but were not formally coded - Patients were more likely to complete follow-up testing when contacted via SMS and phone calls - Staff confidence in coding improved following training - Integrating MyMedicare enrolment into routine workflows increased uptake - Time constraints during consultations remained a barrier to opportunistic coding

- ACT

<Next steps? Record the details of your option under the relevant heading below > ADOPT - Maintain recall systems for follow up testing ADAPT - Allocate protected time for nurses to complete record reviews ABANDON - What did not work?

Evidence of improvement. <Screenshots from extraction tool, Practice Progress Report>

Starting benchmark: As of 15/04 1261 patients have suspected diabetes mellitus but no diagnosis coded.