Practice Name:

| PIP QI quarter: please tick ü | Quarter 1 Nov – Jan ​☐ | Quarter 2 Feb – Apr ☒ | Quarter 3 May – Jul ​ ☐ ​ | Quarter 4 Aug – Oct ​ ☐ |
| --- | --- | --- | --- | --- |
| Date: _________ |  |  |  |  |
| Name of QIA: | Improving patient engagement and reminder systems for GPCCMP reviews. |  |  |  |

| - PLAN |  |  |  |
| --- | --- | --- | --- |
| - Goal | - <What are we trying to accomplish and when? Make the goal simple, measurable, achievable, realistic and timely> - Increase the number of patients with a GPCCMP who complete a review when eligible (every 3 months) from 9 to 150 within 3 months, by implementing structured recall systems and improved booking workflows. |  |  |
| - Baseline Data: | - <What is our current data saying?> - Total GPCCMP patients: 649 - Patients eligible for a review: 635 - Patients with a completed review: 9 - Source: POLAR Clinic Summary Report > MBS > Tracked MBS > Selected TMBS item > GPCCMP |  |  |
| - Data to be Collected: | - <What data will we use to track our improvement?> - We will run monthly POLAR audits to track: - Number of patients who have completed a GPCCMP review - Number of patients overdue for review - Appointment attendance rates for GPCCMP review appointments |  |  |
| - Steps for Implementation |  |  |  |
| - What |  | - Who | - By When |
| - Run POLAR audit to identify patients eligible/overdue for GPCCMP review, cross-check with PRODA, and confirm MyMedicare enrolment status. |  | - Practice manager |  |
| - Embed a reception workflow to book GPCCMP review appointments before patients leave |  | - Reception |  |
| - Implement structured appointment reminders for upcoming and overdue reviews |  | - Reception |  |
| - Provide staff with consistent messaging to educate patients and carers on the importance of GPCCMP reviews |  | - Practice manager |  |

- DO

<Did you do it? Insert any observations you had during implementation of this plan, unforeseen amendments, unexpected events> - Generated a list identifying patients eligible and overdue for GPCCMP review on POLAR, cross-checked with PRODA to confirm reviews completed outside the practice, and reviewed MyMedicare enrolment status - Embedded a reception workflow to ensure GPCCMP review appointments were booked before patients left the practice - Implemented structured appointment reminders for upcoming and overdue reviews, including SMS reminders and follow-up phone calls - Provided staff with consistent messaging and talking points to support patient and carer understanding of the importance of GPCCMP reviews using information from p28-32 of CCM-QI-Workbook_Final-9-July-2025-Adapted-for-CESPHN.pdf

- STUDY

- <Reflections: knowledge gained, effectiveness of improvement, measurement goals, potential changes that could be made in the next cycle> - Increase in GPCCMP reviews completed from 9 to 82 - Reduction in number of patients overdue for review: 553 patients - Booking appointments before patients leave the practice significantly improved review attendance - Structured reminders (SMS + phone follow-up) were more effective than SMS alone - Patients were more likely to attend when provided with clear explanations of the purpose and benefits of GPCCMP reviews - Consistent staff messaging improved patient engagement and understanding

- ACT

<Next steps? Record the details of your option under the relevant heading below > ADOPT - Continue booking GPCCMP review appointments before patients leave the practice ADAPT - Refine reminder timing to optimise attendance rates ABANDON - What did not work?

Evidence of improvement. <Screenshots from extraction tool, Practice Progress Report>

Starting benchmark: As of 11/04 9 out of 635 patients who are eligible for a GPCCMP review have had one completed.