Practice Name:

| PIP QI quarter: please tick ü | Quarter 1 Nov – Jan ​☐ | Quarter 2 Feb – Apr ☒ | Quarter 3 May – Jul ​ ☐ ​ | Quarter 4 Aug – Oct ​ ☐ |
| --- | --- | --- | --- | --- |
| Date: _________ |  |  |  |  |
| Name of QIA: | Identify patients with diabetes who are eligible for GPCCMP |  |  |  |

| - PLAN |  |  |  |
| --- | --- | --- | --- |
| - Goal | - <What are we trying to accomplish and when? Make the goal simple, measurable, achievable, realistic and timely> - Reduce the number of patients who have a diagnosis of diabetes and have never had a GPCCMP from 506 to 400 in 3 months. |  |  |
| - Baseline Data: | - <What is our current data saying?> - Number of active patients with diabetes= 826 - Number of active patients with diabetes who have never had GPCCMP= 506 - POLAR Clinic Summary Report > Clinical > Diagnosis > Select Diabetes from Chronic Disease Category > MBS > Tracked MBS > Selected TMBS Item- GPCCMP > Never had |  |  |
| - Data to be Collected: | - <What data will we use to track our improvement?> - We will run monthly POLAR audits to track: - Number of patients with diabetes eligible for GPCCMP - Number of patients newly commenced on a GPCCMP - Percentage of patients with diabetes on a GPCCMP |  |  |
| - Steps for Implementation |  |  |  |
| - What |  | - Who | - By When |
| - Run POLAR audit to identify patients with diabetes who have never had a GPCCMP |  | - Practice manager |  |
| - Implement a workflow to offer GPCCMPs opportunistically during consultations |  | - GP |  |
| - Introduce a recall system to invite eligible patients to attend practice for GPCCMP |  | - Practice manager |  |
| - Include MyMedicare enrolment as a part of GPCCMP discussions and booking process for eligible patients |  | - Practice manager, reception staff and GP |  |

- DO

<Did you do it? Insert any observations you had during implementation of this plan, unforeseen amendments, unexpected events> - Generated a POLAR report to identify patients with diabetes who were not currently on a GPCCMP and created a working patient list - Developed and maintained a patient register to track eligible patients and monitor follow-up - Introduced opportunistic offering of GPCCMPs during consultations, including chronic disease visits and health assessments - Implemented a recall system (SMS followed by phone calls) to invite eligible patients to attend for GPCCMP - Checked MyMedicare status during GPCCMP discussions and assisted patients to enrol if eligible

- STUDY

- <Reflections: knowledge gained, effectiveness of improvement, measurement goals, potential changes that could be made in the next cycle> - Reduction in number of patients with diabetes who have never had a care plan from 506 to 405 - Opportunistic discussions during routine visits were more effective than recall alone - SMS recalls had moderate response; follow-up phone calls improved engagement - Maintaining a patient register improved tracking and accountability across the practice - Including MyMedicare enrolment within GPCCMP discussions increased patient engagement and uptake

- ACT

<Next steps? Record the details of your option under the relevant heading below > ADOPT - Continue integrating GPCCMP enrolment into GPCCMP workflows ADAPT - Refine patient list to prioritise high-risk patients (e.g. patients with more than one chronic disease) ABANDON - What did not work?

Evidence of improvement. <Screenshots from extraction tool, Practice Progress Report>